## 00_Master_Schedule
AUTO GENERATED / DO NOT EDIT MANUALLY
Date | Day | Person | Project | Site | Schedule / Task | Start Time | End Time | Status | Category | Priority | Remarks | All Day | Source Sheet | Source Row | Last Updated
2026-09-10 | Thu | Suzuki | Project E | Remote | Analysis | 8:30 | 10:30 | Planned | Remote | Medium |  | FALSE | Suzuki | 2 | 2026-09-01
2026-09-10 | Thu | Shiraishi | Project A | Site A | Kickoff | 9:00 | 12:00 | Confirmed | Field | High |  | FALSE | Shiraishi | 2 | 2026-09-01
2026-09-10 | Thu | Tanaka | Project C | Site East | Survey | 9:00 | 11:00 | Confirmed | Field | Medium |  | FALSE | Tanaka | 2 | 2026-09-01
2026-09-10 | Thu | Shiraishi | Project B | Site B | Inspection | 10:00 | 15:00 | Planned | Field | High | Conflict sample | FALSE | Shiraishi | 3 | 2026-09-02
2026-09-11 | Fri | Tanaka | Project C | Site East | Site Support | 9:00 | 18:00 | Confirmed | Field | High |  | FALSE | Tanaka | 3 | 2026-09-02
2026-09-11 | Fri | Shiraishi | Project A | Site A | Documentation | 13:00 | 17:00 | Planned | Office | Medium |  | FALSE | Shiraishi | 4 | 2026-09-03
2026-09-12 | Sat | Suzuki | Project A | Site A | Installation | 9:00 | 17:00 | Confirmed | Field | High |  | FALSE | Suzuki | 3 | 2026-09-02
2026-09-12 | Sat | Tanaka | Project D | Site West | Review | 10:00 | 12:00 | Planned | Office | Medium |  | FALSE | Tanaka | 4 | 2026-09-03
2026-09-14 | Mon | Shiraishi | UNKNOWN | Office | Admin | 9:00 | 18:00 | Confirmed | Office | Low |  | FALSE | Shiraishi | 5 | 2026-09-04
2026-09-14 | Mon | Suzuki | Project A | Site A | Installation | 9:00 | 12:00 | Confirmed | Field | High |  | FALSE | Suzuki | 4 | 2026-09-03
2026-09-14 | Mon | Suzuki | Project B | Site B | Follow-up | 14:00 | 17:00 | Planned | Field | Medium |  | FALSE | Suzuki | 5 | 2026-09-04
2026-09-15 | Tue | Shiraishi | UNKNOWN | UNKNOWN | Paid Leave |  |  | Leave | Leave | High |  | TRUE | Shiraishi | 6 | 2026-09-05
2026-09-16 | Wed | Tanaka | Project A | Site A | Support | 14:00 | 18:00 | Planned | Field | Medium |  | FALSE | Tanaka | 5 | 2026-09-04
2026-09-17 | Thu | Tanaka | UNKNOWN | Office | Internal Meeting | 9:30 | 11:00 | Confirmed | Office | Low |  | FALSE | Tanaka | 6 | 2026-09-05
2026-09-18 | Fri | Suzuki | UNKNOWN | UNKNOWN | Training |  |  | Confirmed | Training | Low |  | TRUE | Suzuki | 6 | 2026-09-05

## 01_Monthly_View
AUTO GENERATED / DO NOT EDIT MANUALLY
Person | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18
Shiraishi | 2026-09-10: Project A / Kickoff 09:00-12:00 Project B / Inspection 10:00-15:00; 2026-09-11: Project A / Documentation 13:00-17:00; 2026-09-14: Admin 09:00-18:00; 2026-09-15: Paid Leave All Day
Suzuki | 2026-09-10: Project E / Analysis 08:30-10:30; 2026-09-12: Project A / Installation 09:00-17:00; 2026-09-14: Project A / Installation 09:00-12:00 Project B / Follow-up 14:00-17:00; 2026-09-18: Training All Day
Tanaka | Project C / Survey 09:00-11:00 | Project C / Site Support 09:00-18:00 | Project D / Review 10:00-12:00 |  |  | Project A / Support 14:00-18:00 | Internal Meeting 09:30-11:00

## 02_Weekly_View
AUTO GENERATED / DO NOT EDIT MANUALLY
Week | Person | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
W37 (2026-09-07) | Shiraishi |  |  |  | Project A / Kickoff 09:00-12:00 Project B / Inspection 10:00-15:00 | Project A / Documentation 13:00-17:00
W37 (2026-09-07) | Suzuki |  |  |  | Project E / Analysis 08:30-10:30 |  | Project A / Installation 09:00-17:00
W37 (2026-09-07) | Tanaka |  |  |  | Project C / Survey 09:00-11:00 | Project C / Site Support 09:00-18:00 | Project D / Review 10:00-12:00
W38 (2026-09-14) | Shiraishi | Admin 09:00-18:00 | Paid Leave All Day
W38 (2026-09-14) | Suzuki | Project A / Installation 09:00-12:00 Project B / Follow-up 14:00-17:00 |  |  |  | Training All Day
W38 (2026-09-14) | Tanaka |  |  | Project A / Support 14:00-18:00 | Internal Meeting 09:30-11:00

## 03_Conflict_Report
AUTO GENERATED / DO NOT EDIT MANUALLY
Person | Date | Schedule A | Schedule B | Project A | Project B | Time A | Time B | Conflict Type | Source Sheet A | Source Row A | Source Sheet B | Source Row B
Shiraishi | 2026-09-10 | Kickoff | Inspection | Project A | Project B | 09:00-12:00 | 10:00-15:00 | CONFLICT | Shiraishi | 2 | Shiraishi | 3

## 04_Availability
AUTO GENERATED / DO NOT EDIT MANUALLY
Date | Person | Availability | Scheduled Minutes | Working Minutes | Notes
2026-09-10 | Shiraishi | PARTIAL | 360 | 540 | Schedules cover part of the workday.
2026-09-11 | Shiraishi | PARTIAL | 240 | 540 | Schedules cover part of the workday.
2026-09-12 | Shiraishi | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-13 | Shiraishi | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-14 | Shiraishi | BOOKED | 540 | 540 | Workday fully covered by schedules.
2026-09-15 | Shiraishi | LEAVE | 540 | 540 | Leave schedule present.
2026-09-16 | Shiraishi | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-17 | Shiraishi | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-18 | Shiraishi | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-10 | Suzuki | PARTIAL | 90 | 540 | Schedules cover part of the workday.
2026-09-11 | Suzuki | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-12 | Suzuki | PARTIAL | 480 | 540 | Schedules cover part of the workday.
2026-09-13 | Suzuki | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-14 | Suzuki | PARTIAL | 360 | 540 | Schedules cover part of the workday.
2026-09-15 | Suzuki | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-16 | Suzuki | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-17 | Suzuki | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-18 | Suzuki | BOOKED | 540 | 540 | All Day schedule present.
2026-09-10 | Tanaka | PARTIAL | 120 | 540 | Schedules cover part of the workday.
2026-09-11 | Tanaka | BOOKED | 540 | 540 | Workday fully covered by schedules.
2026-09-12 | Tanaka | PARTIAL | 120 | 540 | Schedules cover part of the workday.
2026-09-13 | Tanaka | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-14 | Tanaka | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-15 | Tanaka | AVAILABLE | 0 | 540 | No schedules within configured workday.
2026-09-16 | Tanaka | PARTIAL | 240 | 540 | Schedules cover part of the workday.
2026-09-17 | Tanaka | PARTIAL | 90 | 540 | Schedules cover part of the workday.
2026-09-18 | Tanaka | AVAILABLE | 0 | 540 | No schedules within configured workday.