## Schedule
Project ID | Project Name | Site | Project Manager | Task ID | Task Name | Category | Start Date | End Date | Progress % | Status | Resource Count | Assigned Person | Milestone | Dependency | Priority | Last Updated | Remarks
P1 | NRT82 | NRT | Shiraishi | T1 | Design | Engineering | 2026-01-01 | 2026-01-10 | 100 | COMPLETED | 1 | Shiraishi | FALSE |  | MEDIUM | 2026-01-10
P1 | NRT82 | NRT | Shiraishi | T2 | T&C | T&C | 2026-01-11 | 2026-01-20 | 20 | IN_PROGRESS | 2 | Shiraishi,Tanaka | TRUE | T1 | HIGH | 2026-01-15