## Master Schedule
Project Name | Task ID | Task Name | Start Date | End Date | Progress | Status | Delay Status | Days Remaining | Assigned Person | Project Manager | Milestone | Priority | Source File | Source Sheet
NRT82 | T1 | Design | 2026-01-01 | 2026-01-10 | 100 | COMPLETED | ON_TRACK | -242 | Shiraishi | Shiraishi | FALSE | MEDIUM | /home/runner/work/Project-General-manageto/Project-General-manageto/Input/Shiraishi/NRT82/NRT82_schedule.xlsx | Schedule
NRT82 | T2 | T&C | 2026-01-11 | 2026-01-20 | 20 | IN_PROGRESS | DELAYED | -232 | Shiraishi, Tanaka | Shiraishi | TRUE | HIGH | /home/runner/work/Project-General-manageto/Project-General-manageto/Input/Shiraishi/NRT82/NRT82_schedule.xlsx | Schedule

## Project Summary
Project Name | Project Manager | Start Date | End Date | Total Tasks | Completed Tasks | Progress | Delayed Tasks | Milestones | Last Updated | Risk Level | Risk Score
NRT82 | Shiraishi | 2026-01-01 | 2026-01-20 | 2 | 1 | 50 | 1 | 1 | 237 | CRITICAL | 17

## Milestones
Project Name | Task ID | Task Name | End Date | Category
NRT82 | T2 | T&C | 2026-01-20 | T&C

## Delayed Tasks
Project Name | Task ID | Task Name | End Date | Progress | Delay Status
NRT82 | T2 | T&C | 2026-01-20 | 20 | DELAYED

## Resource Conflicts
Person | Date | Projects | Status

## Upcoming 14 Days
Project Name | Task ID | Task Name | Start Date | End Date | Priority | Milestone | Delay Status | Category

## Validation Errors
Severity | Code | Field | Message | Project Name | Task ID | Source File | Source Sheet